## Sheet 1
EXAMPLE BUDGET FOR HIGH COURT APPLICANTS
Milestone | Description | Task | Expenditure Type | Work Required | Estimated Completion Date (DD/MM/YYYY) | Funding Available | Projected Costs | Actual Cost | Balance Remaining | Notes
[6 empty] | A | B | C | A-C
Pre-notification appointment | work undertaken to confirm the applicant/representative has the authority to represent the application group | Appointment process | Project Manager | Preparation of hui |  |  |  |  | 0
|  |  |  | Holding hui |  |  |  |  | 0
|  |  |  | Costs of hui notices |  |  |  |  | 0
|  |  |  | Travel for Project Manager |  |  |  |  | 0
|  |  |  | Accommodation for Project Manager |  |  |  |  | 0
|  | Mandating (as required by High Court) | Project Manager | Preparation of hui |  |  |  |  | 0
|  |  |  | Holding hui |  |  |  |  | 0
|  |  |  | Costs of hui notices |  |  |  |  | 0
|  |  |  | Travel for Project Manager |  |  |  |  | 0
|  |  |  | Accommodation for Project Manager |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
Notification | work undertaken until public notice of the application (under s103) | Project planning and project management | Project Manager | Drafting of public notice(s) |  |  |  |  | 0
|  |  |  | Coordinating with legal counsel |  |  |  |  | 0
|  |  |  | Completing High Court application |  |  |  |  | 0
|  |  |  | Compiling affidavits |  |  |  |  | 0
|  |  |  | Serving court documents |  |  |  |  | 0
|  |  |  | Appointment of Project Manager/Lawyer |  |  |  |  | 0
|  | Publishing public notice | Project Manager | Publication of notice as required by High Court |  |  |  |  | 0
|  | Legal advice | Lawyer | Drafting or approving legal notice |  |  |  |  | 0
|  |  |  | Court fees |  |  |  |  | 0
|  |  |  | Filing fees |  |  |  |  | 0
|  |  |  | Affidavits |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
Pre-hearing and Evidence gathering | work undertaken until hearing commences | Project planning and project management | Project Manager | Coordinating with legal counsel for evidence requirements |  |  |  |  | 0
|  |  |  | Coordinating evidence collection |  |  |  |  | 0
|  | Legal advice and court fees | Lawyer | Drafting and filing court documents |  |  |  |  | 0
|  |  |  | Converting research into evidence |  |  |  |  | 0
|  |  |  | Filing evidence with High Court |  |  |  |  | 0
|  |  |  | Preparation for hearing |  |  |  |  | 0
|  |  |  | Preparation of witnesses |  |  |  |  | 0
|  | Historical research | Historian | Appointment of Historian |  |  |  |  | 0
|  |  |  | Historical research |  |  |  |  | 0
|  | Traditional evidence gathering | Researcher | Appointment of Researcher |  |  |  |  | 0
|  |  |  | Historical research |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
Interlocutory Hearing | (if arising) | Legal advice and court fees | Lawyer | Preparation for Interlocutory Hearing |  |  |  |  | 0
|  |  |  | Attendance at Interlocutory Hearing |  |  |  |  | 0
|  |  |  | Travel |  |  |  |  | 0
|  |  |  | Accommodation |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
Hearing | work undertaken up until hearing concludes | Project planning and project management | Project Manager | Communication with applicant group |  |  |  |  | 0
|  | Legal advice and court fees | Lawyer | Appearance at Hearing |  |  |  |  | 0
|  | Research/expert witness | Historian | Expert witness court appearance |  |  |  |  | 0
|  | Travel and accommodation | Disbursements | Travel |  |  |  |  | 0
|  |  |  | Accommodation |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
Determination | work undertaken until recognition order is sealed | Legal advice and court fees | Lawyer | Analysis of judgement |  |  |  |  | 0
|  |  |  | Legal advice to client |  |  |  |  | 0
|  | Project planning and project management | Project Manager | Coordinating with legal counsel |  |  |  |  | 0
|  |  |  | Administration costs to close claim |  |  |  |  | 0
|  | Drafting of order | Lawyer | Drafting of recognition order |  |  |  |  | 0
|  |  |  | Court fees |  |  |  |  | 0
[5 empty] | Milestone subtotal | 0 | 0 | 0 | 0
2026-08-06
| SIGNED: | SIGNED:
[6 empty] | Total upper funding limit | Total projected costs | Total actual costs
| (Applicant representative) | (MACA representative) |  |  | TOTAL | 0 | 0 | 0
DATE: | / / | / /